## app
|  | Provincial Government of Davao del Sur Annual Procurement Plan for FY 2022 | [11 empty] | Department of Budget and Management Procurement Monitoring Report as of month/day/2006
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
- | Repair/Improvement of PSCB Building located at Provincial Capitol Compound, Matti, Digos City | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - GEN FUND
- | Repair/Improvement of OPAG Building located at Lim/Bataan St., Zone III, Digos City | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - GEN FUND
- | Concreting of FMR at San Isidro Road Section located at Sto. Niño, Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Repair/Improvement of Brgy Gym located at Darapuay, Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 3000000 | 0 | 3000000 | LGDF - 20% Development Fund
- | Concreting of Brgy Road located at Dolo, Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Improvement of Brgy Gym with Construction of Stage located at Poblacion Uno, , Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1200000 | 0 | 1200000 | LGDF - 20% Development Fund
- | Improvement of Tribal Hall located at Poblacion Dos, Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 500000 | 0 | 500000 | LGDF - 20% Development Fund
- | Concreting of Brgy Hall Grounds located at Poblacion Dos, , Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 500000 | 0 | 500000 | LGDF - 20% Development Fund
- | Concreting of FMR from Brgy Union to Buenavista located at Union, Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 10000000 | 0 | 10000000 | LGDF - 20% Development Fund
- | Construction of Multi-Purpose Building (Barangay Hall) located at Libertad, Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 2500000 | 0 | 2500000 | LGDF - 20% Development Fund
- | Concreting of Road from boundary of Tres de Mayo to Sitio Sto. Rosario located at Ruparan, Digos City, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Construction of Hanging bridge located at Goma, Digos City, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 3500000 | 0 | 3500000 | LGDF - 20% Development Fund
- | Concreting of Brgy Road located at Zone 1,Digos City, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 3000000 | 0 | 3000000 | LGDF - 20% Development Fund
- | Repair/Improvement of Brgy Gym at Sambas Subdivision located at Zone 1, Digos City, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1200000 | 0 | 1200000 | LGDF - 20% Development Fund
- | Concreting of Road from District 5 connecting to District 7 to District 4 located at Colorado, Digos City, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 7000000 | 0 | 7000000 | LGDF - 20% Development Fund
- | Concreting of FMR located at Sinayawan, Hagonoy, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 3000000 | 0 | 3000000 | LGDF - 20% Development Fund
- | Riprapping of Shouldering at Purok 6 located at Lanuro, Hagonoy, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Construction of Potable Water System located at Mahayahay, Hagonoy, Davao del Sur | PPDO | NO | Competitive Bidding | - | - | - | - | Others | 2500000 | 0 | 2500000 | LGDF - 20% Development Fund
- | Construction of Potable Water system (additional Source) located at San Gillermo, Hagonoy, Davao del Sur | PPDO | NO | Competitive Bidding | - | - | - | - | Others | 1000000 | 0 | 1000000 | LGDF - 20% Development Fund
- | Repair/Improvement of Brgy Gym located at Aplaya, Hagonoy, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 2000000 | 0 | 2000000 | LGDF - 20% Development Fund
- | Construction of Day Care Center located at Bonifacio, Kiblawan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 2000000 | 0 | 2000000 | LGDF - 20% Development Fund
- | Construction of 2-units Solar Dryers located at Ihan,Kiblawan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - 20% Development Fund
- | Construction of Potable Water Supply System located at Ihan, Kiblawan, Davao del Sur | PPDO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - 20% Development Fund
- | Concreting of FMR located at Manual, Kiblawan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Construction of 3-units Box Culvert at Sikatuna St. located at Poblacion, Kiblawan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 3500000 | 0 | 3500000 | LGDF - 20% Development Fund
- | Construction of Covered Court located at Bagong Silang, Kiblawan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 3500000 | 0 | 3500000 | LGDF - 20% Development Fund
- | Concreting of Road from Purok Santol to Purok Blucon located at Tacul, Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Rehabilitation of Brgy Road located at Mabini, Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 500000 | 0 | 500000 | LGDF - 20% Development Fund
- | Concreting of Road at Boundary New Ilocos to Sitio Simon located at San Isidro, Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Construction of Multi-Purpose Building (Tribal Hall) located at Poblacion, Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 2000000 | 0 | 2000000 | LGDF - 20% Development Fund
- | Construction of Multi-Purpose Building (Barangay Hall) located at Bolton, Malalag, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 2500000 | 0 | 2500000 | LGDF - 20% Development Fund
- | Concreting of FMR located at Bulacan, Malalag, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Construction of Multi Purpose Building (Barangay Hall) located at Caputian, Malalag, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 2500000 | 0 | 2500000 | LGDF - 20% Development Fund
- | Upgrading of Potable Water System located at Tagansule, Malalag, Davao del Sur | PPDO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - 20% Development Fund
- | Concreting of Prov'l Road at Purok 3 located at Sinaragan, Matanao, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Construction of Potable Water System located at Sinawilan, Matanao, Davao del Sur | PPDO | NO | Competitive Bidding | - | - | - | - | Others | 2000000 | 0 | 2000000 | LGDF - 20% Development Fund
- | Repair/Improvement of Brgy Gym located at Sinawilan, Matanao, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - 20% Development Fund
- | Repair/Improvement of Brgy Hall located at Saub, Matanao, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1000000 | 0 | 1000000 | LGDF - 20% Development Fund
- | Construction of Daycare Center located at Cabligan, Matanao, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 2000000 | 0 | 2000000 | LGDF - 20% Development Fund
- | Repair/Improvement of Brgy Gym located at Quirino District, Padada, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - 20% Development Fund
- | Concreting of Brgy Road (from Purok Matulungin-Purok Maligaya B Road Section) - Phase II located at Bato, Padada, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 4000000 | 0 | 4000000 | LGDF - 20% Development Fund
- | Concreting of Sinoron-Ranch Prov'l Road located at Sinoron, Padada, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5050000 | 0 | 5050000 | LGDF - 20% Development Fund
- | Improvement of Brgy Gym located at Parami, Sulop, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1000000 | 0 | 1000000 | LGDF - 20% Development Fund
- | Concreting of Brgy New Cebu-Carre FMR located at New Cebu, Sulop, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund
- | Construction of Provincial Tribal Hall located at Provincial Capitol Compound, Matti, Digos City | PEO | NO | Competitive Bidding | - | - | - | - | Others | 3200000 | 0 | 3200000 | LGDF - 20% Development Fund
- | Construction of Rubberized Oval located at Davao del Sur Sports Cultural and Business Center Complex Compound, Matti, Digos City, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 35000000 | 0 | 35000000 | LGDF - 20% Development Fund
- | Construction of Davao del Sur Provincial Hospital (DSPH) Warehouse located at Zone III, Digos City, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1800000 | 0 | 1800000 | LGDF - 20% Development Fund
- | Development of Davao del Sur Provincial Nursery Agri-Business and Tourism Complex located at Poblacion Dos, Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 7500000 | 0 | 7500000 | LGDF - 20% Development Fund
- | Concreting of Brgy Site Circumferential Road at Purok Neptune located at Managa , Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 10000000 | 0 | 10000000 | LGDF - 20% Development Fund -Peace and Order
- | Repair/Improvement of Brgy Gym located at Kinuskusan , Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - 20% Development Fund -Peace and Order
- | Repair/Improvement of Brgy Hall located at Malabang , Hagonoy, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - 20% Development Fund -Peace and Order
- | Concreting of Paligue-Piape Prov'l Road from National Highway to Romaguera E/S located at Paligue , Hagonoy, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 10000000 | 0 | 10000000 | LGDF - 20% Development Fund -Peace and Order
- | Concreting of Brgy Road (San Isidro-Kibongbong Road Section) located at San Isidro , Kiblawan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund -Peace and Order
- | Construction of Multi-Purpose Building (Barangay Hall) located at Kimlawis , Kiblawan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 3000000 | 0 | 3000000 | LGDF - 20% Development Fund -Peace and Order
- | Concreting of Poblacion - Bacungan Prov'l Road located at Bacungan , Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 9000000 | 0 | 9000000 | LGDF - 20% Development Fund -Peace and Order
- | Concreting of FMR located at Kanapulo , Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 7000000 | 0 | 7000000 | LGDF - 20% Development Fund -Peace and Order
- | Repair/Improvement of Brgy Gym located at Kanapulo, Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 2000000 | 0 | 2000000 | LGDF - 20% Development Fund -Peace and Order
- | Concreting of FMR w/ installation of Box Culvert at Purok 3-B located at Balnate , Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 10000000 | 0 | 10000000 | LGDF - 20% Development Fund -Peace and Order
- | Concreting of Brgy Road located at New Opon , Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | LGDF - 20% Development Fund -Peace and Order
- | Construction Solar Dryer with Mini Warehouse located at Tagaytay , Magsaysay, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - 20% Development Fund -Peace and Order
- | Construction of Multi-Purpose Building (Senior Citizen) located at New Katipunan , Matanao, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 1500000 | 0 | 1500000 | LGDF - 20% Development Fund -Peace and Order
- | Concreting of Matutungan-Bato Prov'l Rd located at Matutungan , Sta. Cruz, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 12000000 | 0 | 12000000 | LGDF - 20% Development Fund -Peace and Order
- | Construction of Evacuation Center located at Tinongtongan, Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 6000000 | 0 | 6000000 | PDRRM FUND - 70%Preparedness and Mitigation Fund
- | Construction of Evacuation Center located at New Clarin, Bansalan, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 6000000 | 0 | 6000000 | PDRRM FUND - 70%Preparedness and Mitigation Fund
- | Construction of Riverbak Protection/ Flood Control System lcoated at Poblacion, Matanao along Public Market, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | PDRRM FUND - 70%Preparedness and Mitigation Fund
- | Construction of Seawall located at Zone III, Sta. Cruz, Davao del Sur | PEO | NO | Competitive Bidding | - | - | - | - | Others | 5000000 | 0 | 5000000 | PDRRM FUND - 70%Preparedness and Mitigation Fund
| Prepared by: |  |  |  | Recommended for Approval: |  |  |  |  | Approved:
| ENGR. SHIELA MAE A. ZAPANTA |  |  |  | DESSAMIE BUAT-SANCHEZ, JD, CPA |  |  |  |  | MARC DOUGLAS IV C. CAGAS
| Head-SBAC Secretariat |  |  |  | SBAC Chairperson |  |  |  |  | Head of Procuring Entity

## how_to_fill_out-definitions
| GUIDE TO PREPARE APP | APP COLUMN HEADER/S
STEP 1 | In the Code column, kindly indicate the PAP Code. Please refer to the code indicated in the technical budget posted in the DBM website. For GOCCs and LGUs, indicate the procuring entity's internal numbering system. | Code (PAP)
STEP 2 | For the Procurement Project column, please align descriptions of program/projects with budget documents and ensure clarity and accuracy in describing each procurement program/project. | Procurement Project
STEP 3 | For PMO/End-User, please indicate the PMO/End-User unit who will implement/utilize the procurement program/project. Multiple end-user units are allowed only if the procurement activity was consolidated by the BAC to procure requirements of the end-user units. | PMO/End-User
STEP 4 | For Mode of Procurement and Schedule for Each Procurement Activity, all modes of procurement are available as a dropdown list and requirements for a specific schedule for Ads/Post of IB/REI, Sub/Open of Bids, Notice of Award, and/or Contract Signing are automatically identified thru the MS Excel formula. Note that for Foreign-funded procurement, please use Others - Foreign-funded procurement as the Mode of Procurement. Kindly indicate a specific period (dates, month, quarter) when each Procurement Activity will be done. Please refer to our website: http://www.gppb.gov.ph/timelines/timelines.htm for the specific periods for each activity. Note: For SVP, IB/REI is similar to RFQ. Ads/Post of IB/REI for Shopping 52.1(b) and NP-SVP (53.9) needs to be posted in PhilGEPS for ABCs above 50k. Notice of Award posting in PhilGEPS is mandatory for all Alternative Modes only for ABCs above 50k. | Mode of Procurement | Schedule for Each Procurement Activity
|  |  | Ads/Post of IB/REI | Sub/Open of Bids | Notice of Award | Contract Signing
STEP 5 | For Source of Funds, a dropdown list is available. If the Source of Funds the PE will use is not included, please indicate "Others" and specify under the Remarks column. | Source of Funds
STEP 6 | For Estimated Budget (PhP), kindly fill out either MOOE or CO columns only. Total ABC column is not editable, but will automatically compute for the total MOOE and CO components of the project. This breakdown is needed for tracking purposes. Finally, please ensure that amounts indicated are aligned with budget documents. | Estimated Budget (PhP)
STEP 7 | Before submission to the GPPB, ensure that the Head of the Procuring Entity (HoPE) approves/signs the APP.
GENERAL INFORMATION
#1 | All Cells with Fill Color Orange needs to be filled out by the Agency. This is a visual reminder of blank or improperly filled out cells.
#2 | To ensure that automated indicator which procurement activity needs to be filled out with specific periods, PE must copy entire Excel row with the mode of procurement for the specific procurement program/project and paste on the last sample row "Negotiated Procurement-53.13" in the template.
#3 | If PE wishes to edit formatting and design of borders, fonts, among others of the APP template, it is suggested to utilize the automated formulas in the template before copying contents and reformatting.
#4 | Per Section of 3.1.1 of DBM Circular No. 2015-7, the Approved Budget for the Contract (ABC) shall be “[t]he amount reflected in the MYOA”. Hence, the ABC in the Annual Procurement Plan (APP) shall be the full amount stated in the MYOA with remarks added on how much will be actually disbursed for that particular fiscal year. Moreover, the Procurement Monitoring Report (PMR) should also reflect full amount in the MYOA if the entire contract was awarded within the fiscal year. Thus, for succeeding years, actual disbursements from the MYOA need not be reflected in the APPs and PMRs, unless current contract with MYOA is terminated and a new procurement activity is undertaken.
DEFINITIONS
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (advertising/posting; submission and receipt/Opening of bids; award of contract; contract signing).
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
7. Estimated Budget - Agency approved estimate of project/program costs
8. Remarks - brief description of program or project

## data_validation (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
Emergency Procurement under the Bayanihan Act
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets
Others - Foreign-funded procurement